## Sheet1
CITS3200 Project Billed Hours Record for Thomas Cleary Each time you do some work on the project, note the week number, start and end date and hour, plus a brief description of the activity. At the end of each week send a copy of the sheet as it currently stands to your group's manager for recording on the group TimeSheet. Date in the form DD/MM/YY and time as XX:YY (24hr clock)
Wk | Begin |  | End |  | Activity | Session Hours | Total Hours
| Date | Time | Date | Time
2 | 2021-08-03 | 15:00 | 2021-08-03 | 15:30 | Created list of questions to ask client about requirements of project for tomorrow's meeting | 0.5 | 0.5 | 0.5
2 | 2021-08-03 | 21:00 | 2021-08-03 | 22:00 | Setup github repo and added weekly deliverable templates | 1 | 1.5 | 1
2 | 2021-08-04 | 9:30 | 2021-08-04 | 10:30 | Group meeting 1 | 1 | 2.5 | 1
2 | 2021-08-04 | 10:30 | 2021-08-04 | 11:30 | Client meeting 1 | 1 | 3.5 | 1
2 | 2021-08-04 | 12:00 | 2021-08-04 | 12:30 | Organising repo files | 0.5 | 4 | 0.5
2 | 2021-08-04 | 12:30 | 2021-08-04 | 13:00 | Email client / auditor / mentor | 0.5 | 4.5 | 0.5
2 | 2021-08-04 | 13:00 | 2021-08-04 | 14:00 | Add project requirements to group timesheet and draft email to client for $100 test | 1 | 5.5 | 1
2 | 2021-08-06 | 21:00 | 2021-08-06 | 21:30 | Organised submission of wk2 deliverables | 0.5 | 6 | 0.5
3 | 2021-08-09 | 13:00 | 2021-08-09 | 15:00 | Worked on sprint1 deliverables - created templates for each document and organised on google drive | 2 | 8 | 2
3 | 2021-08-10 | 21:15 | 2021-08-10 | 21:45 | Finished editing draft sprint 1 deliverables before group works on them / updated tomorrows agenda | 0.5 | 8.5 | 0.5
3 | 2021-08-11 | 9:30 | 2021-08-11 | 10:30 | Team meeting week 3 | 1 | 9.5 | 1
3 | 2021-08-11 | 10:30 | 2021-08-11 | 11:30 | Create spreadsheet of questions we haven't / have asked the client | 1 | 10.5 | 1
3 | 2021-08-11 | 11:30 | 2021-08-11 | 13:00 | Finished preparing slides with chauntelle for audited meeting tomorrow, also finished preparing sprint 1 drafts for meeting - to be completed/assigned tomorrow | 1.5 | 12 | 1.5
3 | 2021-08-11 | 17:00 | 2021-08-11 | 19:00 | Created basic flask application in new repo (to get rid of old commits) | 2 | 14 | 2
3 | 2021-08-11 | 22:15 | 2021-08-11 | 22:45 | Created ERD Diagram and design for DB | 0.5 | 14.5 | 0.5
3 | 2021-08-12 | 17:30 | 2021-08-12 | 18:30 | Attended team meeting week 3 (audited) | 1 | 15.5 | 1
3 | 2021-08-12 | 22:00 | 2021-08-12 | 22:30 | Created google sheet to acquire everyones time availabilties (as they have changed + Qiulan joined) to make sure we can arrange suitable time for next audited meeting with James | 0.5 | 16 | 0.5
0
0
0
0
0
0
0
0
0
0
Wk | Begin |  | End |  | Activity | Session Hours | Total Hours | #VALUE!
| Date | Time | Date | Time |  |  |  | #VALUE!
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Wk | Begin |  | End |  | Activity | Session Hours | Total Hours | #VALUE!
| Date | Time | Date | Time |  |  |  | #VALUE!
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Wk | Begin |  | End |  | Activity | Session Hours | Total Hours | #VALUE!
| Date | Time | Date | Time |  |  |  | #VALUE!
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0